## Implementation Plan v1.4
Phase | Task ID | Description
Phase 1: Foundation & Data (Weeks 1-2) | 1.1 | Finalize v1.4 Data Catalog & Enums: Approve Data Catalog v1.4, including finalized enums for Appwrite, Metadata, Verification Methods, etc.
Phase 1: Foundation & Data (Weeks 1-2) | 1.2 | Implement Firestore Schema Changes: Update `applications` schema (single pass BRE fields), implement `metadata` subcollection structure per Data Catalog v1.4 Sec 4.11, define required indexes (`userId`, `applicationStatus`, `lastUpdatedAt`). Output: Firestore setup aligned with Data Catalog v1.4.
Phase 1: Foundation & Data (Weeks 1-2) | 1.3 | Set up Appwrite Collections: Create `borrower_summary`, `enquiries`, `tradelines` collections based on finalized schema (Data Catalog v1.4 Section 4.6). Set up required indexes (e.g., `panNumber` on enquiries/tradelines). Output: Appwrite collections ready.
Phase 1: Foundation & Data (Weeks 1-2) | 1.4 | Refine Architecture Diagrams: Update system interaction diagrams (like Spec Sec 4.1) to reflect v1.4 single-pass flow, Appwrite 3-collection structure, Firebase Cloud Functions Metadata Orchestrator, metadata subcollection flow, removal of app-side LLM calls. Output: Updated architecture diagrams.
Phase 1: Foundation & Data (Weeks 1-2) | 1.5 | Set up Project Structure for Metadata Orchestrator: Initialize the Firebase Cloud Functions project (TypeScript recommended, following guide in `cloud-functions-guide.txt`). Set up basic file structure (`index.ts`, `metadata/`, `dropoff/`, `utils/`). Output: Basic Cloud Functions project structure ready for implementation.
Phase 2: Core Backend - Single Pass BRE (Weeks 3-5) | 2.1 | Develop Camunda BPMN for Single-Pass Flow: Model process (Start -> Service Task (Call Appwrite via Connector) -> Service Task (Publish External Task for BRE) -> Exclusive Gateway (Evaluate BRE Decision) -> End Events (Approved/Rejected/Referred)). Deploy v1 BPMN model to Camunda. Output: Deployed v1 single-pass BPMN model.
Phase 2: Core Backend - Single Pass BRE (Weeks 3-5) | 2.2 | Implement Camunda <> Appwrite Service Call Logic: Configure Camunda HTTP connector (or similar) within the "Get Bureau Data" Service Task to call the Appwrite API, fetch data from the 3 collections (`borrower_summary`, `enquiries`, `tradelines`) based on PAN. Handle request/response mapping. Output: Bureau data fetch orchestrated by Camunda.
Phase 2: Core Backend - Single Pass BRE (Weeks 3-5) | 2.3 | Develop Python BRE Worker Logic & Rules (Single Pass): Set up worker project using `pyzeebe`. Implement single task handler for `calculateLoanOffer` topic. Code rules logic as detailed in Spec Sec 9.5 (Input Prep, PAN Check, Hard Rules, Risk/Calc, Final Decision including `profileFlag`). Handle I/O based on Data Catalog v1.4 (`breInputData`, `breOutputData`). Output: Python BRE worker v1 ready for deployment.
Phase 2: Core Backend - Single Pass BRE (Weeks 3-5) | 2.4 | Integrate App -> Camunda Trigger: Implement `startLoanProcessAndFetchBureau` call in Android app (`CamundaService.kt`, `CalculateLoanOfferWithBREUseCase.kt`/ViewModel). Securely pass initial required data (e.g., `applicationId`, `userId`). Handle response (instance ID). Output: App can successfully initiate the Camunda loan workflow.
Phase 2: Core Backend - Single Pass BRE (Weeks 3-5) | 2.5 | Integrate App to Receive BRE Results: Implement logic in Android app (ViewModel/Repository, e.g., `LoanOfferViewModel.kt`) to fetch/listen for `breOutputData` updates in the corresponding Firestore `applications` document. Parse results (`decisionStatus`, `profileFlag`, offer parameters). Output: App can receive and react to the BRE decision/offer.
Phase 3: Metadata & Orchestration (Firebase Cloud Functions) (Weeks 4-6) | 3.1 | Implement Metadata Collection Points in Android App: Integrate calls to `MetadataRepository.sendMetadataEvent` at key points (app lifecycle, screen navigation, section completion, document upload/processing events, verification events, errors) as described in Spec Sec 5.3. Ensure payload includes `eventType` and relevant data. Output: App collects metadata, stores locally in subcollection, and triggers Cloud Function endpoint.
Phase 3: Metadata & Orchestration (Firebase Cloud Functions) (Weeks 4-6) | 3.2 | Develop & Deploy Metadata Orchestrator (Cloud Functions): Implement core logic in TypeScript (`processEvent` HTTP function, `dropOffChecker` scheduled function, Firestore interactions, `backgrounded_apps` logic) based on `cloud-functions-guide.txt`. Deploy v1 service to Firebase Functions environment. Output: Orchestrator v1 running and processing events.
Phase 3: Metadata & Orchestration (Firebase Cloud Functions) (Weeks 4-6) | 3.3 | Implement App -> Orchestrator API Communication: Define `MetadataApi.kt` Retrofit interface in App. Implement the HTTP POST call within `MetadataRepositoryImpl.sendMetadataEvent`. Ensure secure communication (HTTPS). Output: App reliably sends events to the Cloud Function endpoint.
Phase 3: Metadata & Orchestration (Firebase Cloud Functions) (Weeks 4-6) | 3.4 | Implement Orchestrator Drop-off Detection Logic (Cloud Function): Implement timer/scheduled task logic (`dropOffChecker`). Implement Firestore queries within the function to check `applications.applicationStatus`, `applications.lastUpdatedAt`, and recent `metadata` events against the `DROP_OFF_TIMEOUT_SECONDS` config. Output: Orchestrator can accurately identify potentially dropped-off applications.
Phase 3: Metadata & Orchestration (Firebase Cloud Functions) (Weeks 4-6) | 3.5 | Integrate Orchestrator -> LLM Call (Drop-off Analysis - Cloud Function): Implement LLM API call logic within `analyzeDropOff` function (TypeScript). Support configurable provider/model (Gemini 1.5 Flash / OpenAI 4o-mini). Securely handle API keys using Cloud Functions environment variables/secrets. Prepare LLM input data; parse JSON/text response. Output: Orchestrator successfully triggers LLM analysis for drop-offs.
Phase 3: Metadata & Orchestration (Firebase Cloud Functions) (Weeks 4-6) | 3.6 | Integrate Orchestrator -> Email Alert (Brevo - Cloud Function): Implement Brevo API call within `sendDropOffEmail` function (TypeScript). Format HTML email content with LLM summary. Securely handle Brevo API key using Cloud Functions environment variables/secrets. Output: Orchestrator sends formatted email alerts for detected drop-offs.
Phase 4: App UI & Bug Fixes (Weeks 6-8) | 4.1 | Implement Specific UI Fixes & Enhancements: Address all UI/UX items from Spec Sec 3.4 (modern back icons, AI bubble positioning, layout adjustments, conditional UI based on employment type, text changes, etc.). Ensure Material 3 adherence. Output: Core UI polished and aligned with requirements.
Phase 4: App UI & Bug Fixes (Weeks 6-8) | 4.2 | Refine Loan Offer Screen Logic: Implement dynamic content display in `LoanOfferScreen.kt` based on `breOutputData.decisionStatus` and `profileFlag` (Approve/Reject/Refer states). Ensure sliders (`LoanOfferSlider.kt`) are correctly enabled/limited. Implement dev-only skip button logic. Output: Loan Offer screen fully functional for single-pass results.
Phase 4: App UI & Bug Fixes (Weeks 6-8) | 4.3 | Refine Application Complete Screen Logic: Implement dynamic content display in `ApplicationCompleteScreen.kt` based on final `applicationStatus` (Approved, Rejected, Under Review). Implement `SuccessConfetti` animation. Output: Final confirmation screen behavior finalized.
Phase 4: App UI & Bug Fixes (Weeks 6-8) | 4.4 | Address Critical Bugs: Fix any remaining `SecurityException` related to FileProvider. Address other P1/P2 bugs identified during development or testing. Output: Major known bugs resolved.
Phase 4: App UI & Bug Fixes (Weeks 6-8) | 4.5 | Remove Bureau Confirmation Screen Code: Delete screen composable, ViewModel, Use Cases, DTOs, and navigation entries related to the removed Bureau Confirmation step. Output: Obsolete Bureau Confirmation code removed.
Phase 4: App UI & Bug Fixes (Weeks 6-8) | 4.6 | Remove App-side LLM Integration Code: Delete `LlmApi.kt`, `LlmService.kt`, related DI modules/dependencies, and any ViewModel logic calling them. Output: Obsolete App-side LLM code removed.
Phase 4: App UI & Bug Fixes (Weeks 6-8) | 4.7 | Remove LinkedIn Integration Code: Delete `LinkedInService.kt`, related ViewModels/Use Cases, UI elements, and dependencies. Output: Obsolete LinkedIn code removed.
Phase 5: Testing (Weeks 8-10) | 5.1 | Unit Testing: Write/execute unit tests covering: Android ViewModels, Use Cases, Repositories, Utils (`InputValidator.kt`); Python BRE rules logic; Firebase Cloud Functions logic (event parsing, drop-off checks). Aim for adequate code coverage. Output: Comprehensive unit test suite.
Phase 5: Testing (Weeks 8-10) | 5.2 | Integration Testing: Perform automated/manual tests for: App<->Firebase (Auth, Firestore R/W incl. subcollections, Storage); App<->Camunda (workflow start); App<->Cloud Functions (event sending); Camunda<->BRE (task assignment/completion); Camunda<->Appwrite (bureau data fetch); Cloud Functions<->Firestore (R/W); Cloud Functions<->LLM (API call/response); Cloud Functions<->Email (API call). Output: Verified component integrations.
Phase 5: Testing (Weeks 8-10) | 5.3 | End-to-End (E2E) Testing: Execute E2E test scripts (manual or automated) covering key user journeys: Successful Approval, Rejection (Hard Rule, Capacity, Profile Flag), Referral, Drop-off Detection & Alerting, Dev Skip Flows. Validate data consistency across all systems. Output: Verified E2E user journeys and system behavior.
Phase 5: Testing (Weeks 8-10) | 5.4 | UI Testing: Manual UI/UX testing across target Android devices/OS versions. Develop automated UI tests (Espresso/Compose). Verify layout responsiveness, navigation, animations, input handling (incl. voice if enabled), and accessibility standards. Output: Validated UI/UX and accessibility compliance.
Phase 5: Testing (Weeks 8-10) | 5.5 | Security Audit: Conduct Static Application Security Testing (SAST), Dynamic Application Security Testing (DAST), software composition analysis (dependency scanning), API security testing (App, Camunda, Cloud Functions, Appwrite endpoints), infrastructure review, secrets management audit. Output: Security vulnerabilities identified and addressed/mitigated.
Phase 6: Deployment & Monitoring (Week 11) | 6.1 | Prepare Release Builds: Generate signed Android release builds (APK/AAB). Package final backend components (Camunda BPMN, Dockerized Python BRE, Cloud Functions deployment package). Output: Production-ready artifacts.
Phase 6: Deployment & Monitoring (Week 11) | 6.2 | Deploy Updated Backend Components: Deploy final Camunda BPMN model, Python BRE container image, Firebase Cloud Functions service to the production environment. Apply production configurations (API keys, endpoints, timeouts, scaling settings). Output: Backend services deployed and configured for production.
Phase 6: Deployment & Monitoring (Week 11) | 6.3 | Configure Production Monitoring & Alerting: Set up monitoring dashboards (e.g., Firebase Console, Cloud Monitoring, Camunda Operate, Appwrite Console) and alerts based on Spec Sec 10.3 (incl. Cloud Functions metrics like invocations, execution time, errors). Verify alert routing (e.g., PagerDuty, email). Output: Production monitoring and alerting configured and verified.
Phase 6: Deployment & Monitoring (Week 11) | 6.4 | Go-live & Post-launch Monitoring: Initiate gradual Play Store rollout for the Android App. Closely monitor system health, application performance, business metrics, and error logs during and after rollout. Be prepared to execute rollback plan if critical issues arise. Output: Application v1.4 live in production; ongoing monitoring established.