## Implementation Plan
Phase | Task ID | Description | Status
Phase 1: Foundation & Data | 1.1 | Finalize v1.3 Data Catalog & Enums: Approve Data Catalog v1.3, including finalized enums. | Finalised
Phase 1: Foundation & Data (Weeks 1-2) | 1.2 | Implement Firestore Schema Changes: Update applications schema (single pass BRE fields), implement metadata subcollection structure, define indexes. Output: Firestore setup aligned with Data Catalog v1.3.
Phase 1: Foundation & Data (Weeks 1-2) | 1.3 | Set up Appwrite Collections: Create borrower_summary, enquiries, tradelines collections. Define initial schema (note enquiries pending sample report). Set up indexes. Output: Appwrite collections created.
Phase 1: Foundation & Data (Weeks 1-2) | 1.4 | Refine Architecture Diagrams: Update system interaction diagrams to reflect v1.3 single-pass flow, Appwrite structure, metadata flow, removal of direct App-LLM calls. Output: Updated diagrams.
Phase 1: Foundation & Data (Weeks 1-2) | 1.5 | Set up Project Structure for Metadata Orchestrator: Initialize the codebase/repository (e.g., Cloud Function project, Lambda setup). Output: Basic project structure ready.
Phase 2: Core Backend - Single Pass BRE | 2.1 | Develop Camunda BPMN for Single-Pass Flow: Model process (Start -> Get Bureau -> BRE Task -> Gateway -> End). Configure connectors/tasks. Deploy v1 BPMN model. Output: Deployed v1 BPMN model.
Phase 2: Core Backend - Single Pass BRE (Weeks 3-5) | 2.2 | Implement Camunda <> Appwrite Service Call Logic: Configure Camunda HTTP connector for Appwrite API call (3 collections). Handle request/response. Output: Bureau data fetch orchestrated by Camunda.
Phase 2: Core Backend - Single Pass BRE (Weeks 3-5) | 2.3 | Develop Python BRE Worker Logic & Rules (Single Pass): Set up worker project (pyzeebe). Implement single task handler (calculateLoanOffer). Code rules per Spec Sec 9.5. Handle I/O per Data Catalog v1.3. Output: BRE worker v1 ready.
Phase 2: Core Backend - Single Pass BRE (Weeks 3-5) | 2.4 | Integrate App -> Camunda Trigger: Implement startLoanProcessAndFetchBureau call in Android app (CamundaService.kt, Use Case/VM). Pass initial data securely. Output: App can initiate Camunda workflow.
Phase 2: Core Backend - Single Pass BRE (Weeks 3-5) | 2.5 | Integrate App to Receive BRE Results: Implement logic in Android app (VM/Repo) to fetch/listen for breOutputData. Parse results. Output: App can receive and display BRE decision/offer.
Phase 3: Metadata & Orchestration | 3.1 | Implement Metadata Collection Points in Android App: Capture events (device, session, screens, sections, docs, verification, errors). Save events to Firestore metadata subcollection. Output: Metadata collection implemented; data saved.
Phase 3: Metadata & Orchestration (Weeks 4-6) | 3.2 | Develop & Deploy Metadata Orchestrator Service: Implement core logic (HTTP endpoint, parsing, timer logic, Firestore queries) as Cloud Function/Lambda. Deploy v1 service. Output: Orchestrator v1 running.
Phase 3: Metadata & Orchestration (Weeks 4-6) | 3.3 | Implement App -> Orchestrator API Communication: Define/implement OrchestratorApi.kt Retrofit interface. Implement sendEvent calls in app. Ensure secure comms. Output: App sends events to Orchestrator.
Phase 3: Metadata & Orchestration (Weeks 4-6) | 3.4 | Implement Orchestrator Drop-off Detection Logic: Implement timer/scheduled task logic. Implement Firestore queries to check status/timestamps. Output: Orchestrator can identify drop-offs.
Phase 3: Metadata & Orchestration (Weeks 4-6) | 3.5 | Integrate Orchestrator -> LLM Call (Drop-off Analysis): Implement LLM API call logic (configurable provider/model: Gemini 2.0 Flash / OpenAI 4O-mini). Handle API keys securely. Prepare input data; parse response. Output: Orchestrator triggers LLM analysis.
Phase 3: Metadata & Orchestration (Weeks 4-6) | 3.6 | Integrate Orchestrator -> Email Alert (Brevo): Implement Brevo API call. Format email content. Handle API keys securely. Output: Orchestrator sends email alerts.
Phase 4: App UI & Bug Fixes | 4.1 | Implement Specific UI Fixes & Enhancements: Address all items in Spec Sec 3.4 (back arrows, AI bubble, layouts, conditional UI, etc., excluding Bureau Conf screen). Ensure M3 adherence. Output: Core UI polished.
Phase 4: App UI & Bug Fixes (Weeks 6-8) | 4.2 | Refine Loan Offer Screen Logic: Implement dynamic display based on single-pass breOutputData. Implement slider logic for 'Refer' case. Implement dev-only skip button. Output: Loan Offer screen finalized.
Phase 4: App UI & Bug Fixes (Weeks 6-8) | 4.3 | Refine Application Complete Screen Logic: Implement dynamic content based on final applicationStatus. Output: Final confirmation screen finalized.
Phase 4: App UI & Bug Fixes (Weeks 6-8) | 4.4 | Address Critical Bugs: Fix FileProvider SecurityException. Address other critical bugs. Output: Major known bugs resolved.
Phase 4: App UI & Bug Fixes (Weeks 6-8) | 4.5 | Remove Bureau Confirmation Screen Code: Delete screen file, VM, Use Cases, DTOs, navigation entries. Output: Obsolete Bureau Confirmation code removed.
Phase 4: App UI & Bug Fixes (Weeks 6-8) | 4.6 | Remove App-side LLM Integration Code: Delete LlmApi.kt, LlmService.kt, related DI/dependencies. Remove calls from VMs. Output: Obsolete App-side LLM code removed.
Phase 4: App UI & Bug Fixes (Weeks 6-8) | 4.7 | Remove LinkedIn Integration Code: Delete LinkedInService.kt and related code/dependencies. Output: Obsolete LinkedIn code removed.
Phase 5: Testing | 5.1 | Unit Testing: Write/execute unit tests (Android VMs/Use Cases/Repos, BRE rules, Orchestrator logic). Output: Unit test suite with adequate coverage.
Phase 5: Testing (Weeks 8-10) | 5.2 | Integration Testing: Perform tests (App<->Firebase, App<->Camunda, App<->Orchestrator, Camunda<->BRE, Camunda<->Appwrite, Orchestrator<->LLM, Orchestrator<->Email). Output: Verified integrations.
Phase 5: Testing (Weeks 8-10) | 5.3 | End-to-End (E2E) Testing: Execute E2E scripts for key flows (Approve, Reject, Refer, Drop-off, Skips). Validate data consistency. Output: Verified E2E user journeys.
Phase 5: Testing (Weeks 8-10) | 5.4 | UI Testing: Manual UI/UX testing across devices/OS. Develop automated UI tests (Espresso/Compose). Verify accessibility. Output: Validated UI/UX and accessibility.
Phase 5: Testing (Weeks 8-10) | 5.5 | Security Audit: Conduct SAST, DAST, dependency scanning, API testing, infra review, secrets audit. Output: Security vulnerabilities identified/addressed.
Phase 6: Deployment & Monitoring | 6.1 | Prepare Release Builds: Generate signed Android release builds (APK/AAB). Package final backend components. Output: Production-ready artifacts.
Phase 6: Deployment & Monitoring (Week 11) | 6.2 | Deploy Updated Backend Components: Deploy final Camunda BPMN, Python BRE image, Metadata Orchestrator service to production. Apply production configs. Output: Backend services deployed to production.
Phase 6: Deployment & Monitoring (Week 11) | 6.3 | Configure Production Monitoring & Alerting: Set up dashboards/alerts per Spec Sec 10.3. Verify alert routing. Output: Production monitoring/alerting configured.
Phase 6: Deployment & Monitoring (Week 11) | 6.4 | Go-live & Post-launch Monitoring: Initiate gradual Play Store rollout. Monitor systems/metrics closely. Be ready for rollback. Output: Application live; ongoing monitoring established.